MEETCOMBO

2026-2027 Operating Plan

Foundation first. Evidence before investment. Systems that survive disruption.

Plan start: Thursday, July 16, 2026 | Virtual Fleet Day 1

# 1. The Core Operating Thesis

MeetCombo is an AI operating system for building and operating businesses. It acts as an evidence engine: observe, think, simulate, launch, operate, and improve.

Before money is invested, MeetCombo creates a virtual version of the business, runs the numbers, records the assumptions, tracks live market evidence, stress-tests the model, and produces a go/no-go decision.

The first complete case study is a virtual vehicle-rental company. Its first comparison fleet is a Toyota Sienna, the existing 2024 Tacoma SR 4x4, a Camry Hybrid, and a GR Supra. The winning vehicle may receive a real 90-day pilot after the virtual trial.

GitHub remains the source of truth. Conversations become decisions, procedures, dashboards, daily logs, and reusable operating playbooks rather than disappearing inside chat history.

# 2. The Four Connected Engines

| Engine | Primary Job | Near-Term Return | Long-Term Asset |
| --- | --- | --- | --- |
| Toyota Sales | Stable income, customer service, lead generation, deal intelligence | More appointments, follow-up, referrals and sales | Sales playbooks and automotive intelligence |
| Raised Outside | Document life, fatherhood, outdoor travel and products | Content library, product placement and audience growth | Founder-led outdoor brand and community |
| MeetCombo | Research, simulate, document and operate businesses | Immediate productivity and decision support | Productized AI operating system |
| Virtual Fleet | Validate rental economics before buying | Avoid bad purchases and identify best vehicle | First evidence-engine case study |

# 3. Non-Negotiable Foundation Rules

No vehicle purchase until the virtual model passes the full gate.

Every assumption must have a source, date, owner, and confidence rating.

Free or discounted labor is still assigned a realistic cost. Detailing is budgeted at $50-$100 per turn until actual costs prove otherwise.

No business depends on one person, one platform, one customer source, or one exceptional month.

No private customer data is copied into unapproved AI tools. CRM integrations must use authorized access, minimum necessary data, audit logs, and written dealership approval.

Every new workflow is first documented manually, then automated only after it works.

Cash flow, custody stability, parenting time, sleep, and core employment outrank unnecessary expansion.

Raised Outside and MeetCombo remain separate brands: Raised Outside is the public lifestyle/product brand; MeetCombo is built privately as the operating system.

# 4. The 90-Day Virtual Fleet Experiment

Trial window: July 16-October 13, 2026. A 30-day setup period is contained inside the 90-day experiment; it is not an additional delay.

## Virtual Vehicles

Toyota Sienna LE/XLE - primary family and airport hypothesis

2024 Toyota Tacoma SR 4x4 - owned-asset comparison, subject to financing and insurance permission

Toyota Camry Hybrid - economy, reliability and fuel-savings hypothesis

Toyota GR Supra 3.0 automatic - halo/experience vehicle hypothesis

## Daily Evidence Collected

Advertised and estimated realized daily price

Available versus unavailable dates

Trip and review growth

Minimum days, discounts and mileage allowance

Delivery zones, airport fees, parking and travel time

Vehicle purchase price, payment, warranty, protection products and depreciation

Insurance, platform plan, deductible exposure and downtime

Cleaning, maintenance, tires, brakes, fuel, tolls and labor

Local events, tourism, replacement-rental demand and seasonality

Social comments, direct messages, searches and questions indicating demand

## Booking Classification

Each potential booking receives one status: Likely Won, Competitive, Unlikely, or Insufficient Evidence. Competitor unavailability alone never counts as a booking. The model begins with a no-review penalty and earns stronger conversion assumptions only as the simulated listing improves.

## Financial Gate

At least 15 realistically bookable days per month.

Positive operating cash flow after platform share, payment, insurance, detailing, delivery, maintenance, depreciation, taxes, reserves and labor.

Positive contribution in a scenario with bookings reduced by 20%.

A minimum reserve covering three months of fixed expenses, the selected protection-plan exposure, one set of tires, and an additional operating buffer.

A repeatable delivery and cleaning process that does not damage Toyota performance, parenting time, or sleep.

A reasonable annual return on invested cash. A fixed 20% monthly ROI is rejected as an unrealistic universal requirement; the dashboard will show cash-on-cash return, annualized ROI, margin and payback period.

# 5. Virtual Sienna Deal - Day 1 Assumptions

The Sienna will be treated as virtually purchased on July 16, 2026. The exact VIN and listing will be selected during the first seven days. Until then, the model uses a new LE at MSRP as the baseline and adds actual local quotes when available.

| Item | Rule |
| --- | --- |
| Purchase target | New Sienna LE at MSRP, plus verified dealer-installed items only |
| Tax and registration | Use actual Florida/Volusia treatment from the buyer order; temporary planning placeholder only until verified |
| Fees | $1,200 placeholder: $400 tag/registration plus $800 unknown-fee buffer |
| APR | 7.0% planning rate |
| Term scenarios | 60 and 72 months; business decision uses total interest and cash flow, not payment alone |
| Down payment scenarios | 10%, 20%, and cash-equivalent business capital |
| Protection | Price warranty/service agreement, tire-and-wheel, GAP where relevant, and commercial-use eligibility in writing |
| Detailing | $50-$100 per completed trip until actual outsourced or internal cost is measured |
| Virtual closing date | July 16, 2026 |

# 6. Toyota Sales: Immediate MeetCombo ROI

MeetCombo first proves value by helping Caleb sell more cars without violating dealership policies or customer privacy.

Daily follow-up queue: unsold showroom traffic, sold-customer check-ins, referral requests, lease maturities, warranty expirations and upgrade opportunities.

Lead-source intelligence: dealership CRM, approved Automotive Mastermind workflows, AutoTrader and authorized campaign results.

Public-market prospecting: identify Facebook Marketplace and other public listings that may indicate trade interest, but do not scrape prohibited data, misrepresent identity, or contact people outside platform and dealership rules.

Deal review: Caleb can provide redacted worksheets or screenshots so MeetCombo learns the process without receiving unnecessary personal customer information.

Content-to-lead system: vehicle walkarounds, ownership education, comparisons, payment explanations and customer-care follow-ups.

Referral standard: ask because the customer was cared for, and promise to take equally good care of the person they send.

# 7. Raised Outside: 90-Day Content System

Raised Outside does not need Caleb to pretend to be a travel guru. The story is a father building businesses, stability and memories with Willow while learning to live more intentionally outdoors.

Order a small first merchandise batch immediately: enough shirts for repeated filming and product placement, not a large inventory gamble.

Create one month of stock footage during the 90-day period: family travel, Florida outdoors, camp setup, driving, packing, detailing, working, product close-ups and quiet founder moments.

First anchor video: Devil's Den overnight trip with Mom and Willow, wearing Raised Outside merchandise and documenting the full experience.

Publish from repeatable content pillars: fatherhood, Florida adventures, Toyota/vehicle knowledge, building businesses, learning systems, products and behind-the-scenes progress.

Protect Willow's privacy and safety: avoid real-time location posting, school/routine details, legal-case commentary, and content that she may later find embarrassing or invasive.

# 8. Calendar: Tonight Through Year-End 2026

| Date | Focus | Deliverables |
| --- | --- | --- |
| Tonight - Thu Jul 16 | Foundation lock | Create GitHub-ready plan; open Virtual Fleet Day 1; create Sienna/Tacoma/Camry/Supra folders; define scorecard; make Raised Outside shirt order shortlist; create tomorrow Toyota lead list. |
| Fri Jul 17-Sun Jul 19 | Select the baseline | Find 3 real Sienna candidates; request/estimate buyer orders; choose one virtual VIN; draft mock listing; record Tacoma constraints; outline Devil's Den video. |
| Jul 20-Jul 31 | Build the machine | Collect daily competitor snapshots; establish operating costs; draft sales follow-up workflows; order shirts; capture first stock footage; document every repeated decision. |
| August | Evidence + production | Run daily virtual bookings; publish/prepare consistent Raised Outside content; test Toyota lead routines; validate delivery zones and detailing workflow; complete first monthly virtual-fleet close. |
| September | Stress test + consistency | Continue tracking; run 20% demand-down scenario; compare Sienna/Tacoma/Camry/Supra; improve content based on audience signals; remove workflows that create overload. |
| Oct 1-Oct 13 | Finish virtual trial | Complete 90-day dataset, reconcile assumptions, produce ranked fleet and go/no-go recommendation. |
| Oct 14-Oct 31 | Decision month | Audit data quality; select real pilot only if gate passes; otherwise extend or reject without emotional attachment. |
| November | Build or refine | If approved, prepare entity, insurance, financing, SOPs and launch assets. If rejected, rerun the strongest alternative. Continue Toyota and Raised Outside systems. |
| December | Year-end close | Review income, audience, custody-supporting stability, operating documentation and 2027 capital plan. Freeze unnecessary new projects for year-end cleanup. |

# 9. Weekly Operating Rhythm

| Cadence | Action |
| --- | --- |
| Daily - 15 min | Update virtual-fleet prices/availability; capture one Toyota lead action; log one decision or lesson. |
| Workdays | Toyota income first: appointments, follow-up, referrals and approved CRM work. |
| One evening | MeetCombo systems: clean data, update GitHub, automate only proven steps. |
| One filming block | Raised Outside stock footage or anchor-video production. |
| Sunday review | Family/calendar check, virtual fleet scorecard, content queue, cash plan and next-week priorities. |

# 10. 2027 Roadmap

| Quarter | Outcome |
| --- | --- |
| Q1 2027 | Run the first real vehicle pilot only if approved; compare predicted versus actual bookings, costs, labor, damage and reviews; retrain the model with reality. |
| Q2 2027 | Decide whether to add vehicle two, extend vehicle one, or exit. Productize the virtual-business validation framework for another MeetCombo business experiment. |
| Q3 2027 | Expand recurring revenue, content distribution and approved business integrations. Create repeatable onboarding for a second operator or client. |
| Q4 2027 | Evaluate whether MeetCombo is ready for a controlled external beta. Preserve GitHub documentation, ownership, privacy boundaries and clear agreements with collaborators. |

# 11. Storm-Resistance: Expected Failure Modes

| Risk | Resistance |
| --- | --- |
| Overload | Limit active fronts to Toyota income, Raised Outside content, MeetCombo documentation and the virtual fleet. New ideas go to backlog. |
| Bad data | Store source URL, date, screenshot or note, assumptions and confidence. Never treat unavailable dates as confirmed bookings. |
| Privacy/compliance | Use dealership-approved systems only; redact deal documents; obtain written approval before CRM or Automotive Mastermind integrations. |
| Platform dependence | Keep business logic, SOPs and data in GitHub. Turo, social networks, School of Grit systems and AI providers are replaceable tools. |
| Mentor/IP confusion | Learn from Corey and School of Grit, but document ownership, permissions, testimonials, confidential information and commercial terms before joint work. |
| Cash-flow shock | Do not count projected rental income before launch; maintain reserves; avoid high-interest revolving debt for vehicles. |
| Custody or family disruption | Use flexible filming and system blocks; maintain work stability and a documented routine; never make the businesses dependent on Mom moving to Florida. |
| Health/burnout | Protect sleep, parenting and work performance; minimum viable daily progress beats unstable sprints. |
| Emotional attachment to a vehicle | The scorecard selects the winner. A favorite vehicle can lose. |
| Legal/insurance surprise | No listing or purchase until title, lender, warranty/service contract, commercial use and insurance are confirmed in writing. |

# 12. GitHub Source-of-Truth Structure

/docs/CHATGPT_HANDOFF.md
/docs/CHANGELOG.md
/docs/TODO.md
/docs/DECISIONS.md
/docs/roadmaps/2026-2027-operating-plan.md
/docs/daily/2026/07/2026-07-16.md
/experiments/virtual-fleet/README.md
/experiments/virtual-fleet/data/
/experiments/virtual-fleet/vehicles/sienna/
/experiments/virtual-fleet/vehicles/tacoma/
/experiments/virtual-fleet/vehicles/camry-hybrid/
/experiments/virtual-fleet/vehicles/supra/
/playbooks/toyota-sales/
/playbooks/raised-outside-content/

This file is GitHub-ready, but it has not been pushed because no GitHub connection is available in this chat. The accompanying Markdown file can be copied directly into /docs/roadmaps/2026-2027-operating-plan.md.

# 13. Tonight's Exact Checklist

Create the GitHub folders and copy the Markdown plan into /docs/roadmaps/.

Add the core thesis to CHATGPT_HANDOFF.md: MeetCombo validates businesses virtually before capital is invested.

Create Virtual Fleet Day 1 with July 16, 2026 as the virtual closing date.

Open four vehicle records: Sienna, Tacoma, Camry Hybrid and Supra.

Record the temporary Sienna assumptions: MSRP baseline, 7% APR, fee buffer, $50-$100 detailing, 60/72-month scenarios.

At Toyota, identify up to three real Sienna candidates or obtain the current new LE MSRP/buyer-order structure.

Write tomorrow's top 10 sales follow-ups/referral opportunities using only approved customer data.

Choose the first Raised Outside shirt quantity and designs needed for filming; do not over-order.

Create the Devil's Den shot list and a private family/privacy checklist.

End the night by selecting the three highest-value actions for Friday. No additional projects are started.

# 14. Verified Guardrails

Current official sources confirm the planning guardrails below. Exact commercial-use eligibility must still be verified in the specific contracts before purchase or listing.

Toyota new-vehicle basic coverage is generally 36 months/36,000 miles, while powertrain coverage is generally 60 months/60,000 miles.

Toyota Gold Certified currently advertises a 12-month/12,000-mile limited comprehensive warranty and a 7-year/100,000-total-vehicle-mile limited powertrain warranty, subject to program terms.

Florida law assigns specified liability responsibilities to peer-to-peer car-sharing programs during the sharing period, with exceptions. That is not a substitute for contract review or off-trip coverage.

Florida imposes a peer-to-peer car-sharing surcharge collected by the program for applicable sharing periods.

## Official source references

Toyota warranty support: https://support.toyota.com/s/article/What-warranty-coverag-7683

Toyota Certified warranty: https://www.toyotacertified.com/warranty

Florida peer-to-peer liability statute: https://www.leg.state.fl.us/statutes/index.cfm?App_mode=Display_Statute&URL=0600-0699%2F0627%2FSections%2F0627.7483.html

Florida car-sharing surcharge statute: https://www.leg.state.fl.us/statutes/index.cfm?App_mode=Display_Statute&URL=0200-0299%2F0212%2FSections%2F0212.0606.html